## Phase I
Req ID* | Requirement Title | Acceptance Criteria* | Priority* | Approved (LOB) | Date Submitted | Notes | Questions
1 | Ability to create and manage accounts for clients | Name, email address, password, Usernmae, Birthdate, Gender, City, State, Country, Time Zone Ability to upgrade to premium version for a price (credit card information) | Critical
1.1 | Ability to log into an existing account with credentials |  | Critical
1.2 | 2-factor authentication, until user saves recognized device |  | Medium
2 | Identify a users location based on where they log in from |  | High |  |  | Request access to users location
3 | Ability to create a new party or event from a user | 1. Create a public or a private party (Name of) 2. Determine number of attendees 3. Choose a date & time 4. Location 5. Write a description 6. Ability to post updates (similar to FB) 7. Track the number of attendees signed up 8. List co-hosts 9. Allow guests to invite friends 10. Categorize the party | Critical |  |  | Need to be able to limit or authenticate for security (college parties: cops, townies, etc.)
4 | Have the capability to go through a tutorial process and identify interests, hobbies, likes/dislikes, etc. | Store ongoing habits of a returning user to buid a history for recommendations, push notifications | High
5 | Search capabilities to find parties near users location. Possibly categorize parties based on city or college for easier searching. | Provide flexibility with searches: Expand or constrict geo radius, etc. | Critical
6 | Provide users ability to filter parties or events based on categories of what the user is looking for | 1. College Party 2. House Party 3. Block Party 4. Family Party (Birthday, Holiday, Dinner) 5. Graduation Party 6. Public Party (Alive at 5, Rockin on the River, etc.) 7. Bachelor Party 8. Dance Party 9. Cocktail Party 10. Phase II and III "events" 11. Fundraisers | High
7 | Integrate a payment system, so that hosts can charge attendees | PayPal, Venmo, MasterPass | Low
8 | Store and maintain user data without expiration | DB will not purge data | Critical
9 | Easy integration for local businesses, companies, and applications | Restaurants, bars, clubs, AirBnB, hotels, fitness centers….. Application could support a companies capacity management by offering open timeslots, tracking how many people signed up, and limiting based on company predetermined max capacity | High
10 | Directly integrate with phone GPS to navigate user to the desired location or party |  | Nice To Have
11 | Create a trending or trends section for popular or current events/parties in the area |  | Medium
12 | Allow an "interest level" function for users to rate interest in an event on scale of 1 - 10 |  | Nice To Have
13 | Maintain history of past events that user has signed up for, attended, or rated |  | High
14 | Allow a "Share" capability to easily send an event or listing via text, email, snapchat, app itself, Dropbox, FB?? |  | Low
15 | Ability to generate reports for employees about overall trending, interests, geography, user metadata | Report functionality off of DBMS | Medium
16 | Application will send out alerts if an error/issue arises | Employees are notified when an issue/error occurs | High
17 | System will have proper code management and version controls | VCS, PPM code management controls | Critical

## Phase II
Events outside of parties (Hiking, Rock Climbing, Trampoline Parks, Concerts, Racetracks, Nature Walks, Block Parties, Bars, Restaurants, boat day [Lake George])

## Phase III
RSVP capabilities for parties and events (weddings, baptisms, grad parties, etc.)
Group finders if people don’t want to do something alone